## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Color
PROJECT TITLE
Team Freeza |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Liam, Maraea, Kyle
Project Start Date: | 2026-02-17 |  |  |  |  | March | [6 empty] | April | [27 empty] | May
Scrolling Increment: | 40 | time axis 2026-03-29 to 2026-05-23
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-03-29 to 2026-05-23
Iteration 1
Set up GitHub and learn Git | On Track | Team | 100% | 2026-02-17 | 6
GitHub Repository | Milestone | Liam | 100% | 2026-02-23 | 1
Meeting 1 | Goal | Team | 100% | 2026-02-24 | 1
Personas | Med Risk | Kyle, Maraea | 100% | 2026-02-23 | 20
Meeting 2 | Goal | Team | 100% | 2026-03-03 | 1
Stakeholder Register | Low Risk | Kyle, Liam | 100% | 2026-02-23 | 20
Meeting 3 | Goal | Team | 100% | 2026-03-10 | 1
Iteration 1 Completion | Milestone | Team | 100% | 2026-03-19 | 1
Iteration 2
Kanban Board | Med Risk | Kyle, Maraea | 100% | 2026-03-20 | 15
Resource Requirements | Med Risk | Kyle | 100% | 2026-03-30 | 15
Gantt Chart | Med Risk | Liam | 70% | 2026-04-09 | 16
Progress Report | High Risk | Team | 10% | 2026-04-22 | 7
Iteration 2 Completion | Milestone | Team | 50% | 2026-04-29 | 1 | bar: 2026-04-29
Website development
Low fidelity wireframe | Low Risk | Mai, Yoan, Jovica | 100% | 2026-05-01 | 2
Wireframe review | Goal | Dev team | 100% | 2026-05-03 | 0.5
Wireframe finalizing | Milestone | Mai, Yoan | 100% | 2026-05-04 | 2
Graphic Design | Med Risk | Mai | 100% | 2026-05-06 | 3
Back-end | High Risk | Nomthandazo | 100% | 2026-05-09 | 3 | bar: 2026-05-22
Front-end | Med Risk | Oinatz | 100% | 2026-05-12 | 3
Website test phase 1 | Med Risk | Mai, Damo | 100% | 2026-05-15 | 1
Website test phase 2 | Low Risk | Gov, Melitta | 100% | 2026-05-16 | 1
Website test phase 3 | Low Risk | Ramesh | 100% | 2026-05-17 | 1
Fixing | Med Risk | Nomthandazo, Oinatz, Melitta | 100% | 2026-05-18 | 3
Website version 1.0 completion | Milestone | Dev team | 100% | 2026-05-21 | 19.5
Iteration 3
Risk Register | Med Risk |  | 0% | 2026-04-30 | 7
Upload Website Files | Med Risk |  | 0% | 2026-05-05 | 7
Integration | Med Risk |  | 0% | 2026-05-10 | 7
User Acceptance Test | Med Risk |  | 0% | 2026-05-15 | 7
Iteration 3 Complete | Milestone |  | 0% | 2026-05-22 | 1
END
To add more data, Insert new rows ABOVE this one