## Sheet1
When: 03/06/2021 09:00 AM |  | Who: Myname | Application: ParkMate
Note: please make sure you fill all information related to your project below and convert/include link to Wiki Or readme.md (GitHub)
ID | Scenario Title | Status | Scenario | Remarks
1 | Home Page Load | Pass | Clicked link, website loaded properly onto home page | As expected
2 | Page Scroll | Pass | Can scroll and move on the home page | As expected
3 | Watches Navigation | Pass | Clicking Watches takes user to Latest Watches section | As expected
4 | View All Button | Failed | Clicking View All simply reloads the page | Not expected — should navigate to full watches listing
5 | Watch Item Click | Failed | Clicking any of the watches reloads the page | Not expected — should open watch detail page
6 | Top Bar Label | Failed | Top bar had Watches replaced with Products | Not expected — label should remain as Watches
7 | About Page Navigation | Pass | Clicking About loads the About page | As expected
8 | About Us Section Display | Pass | Displays a small About Us section on the page | As expected
9 | Contact Info Links | Failed | Clicking any of the contact us information simply reloads the page | Not expected — should open phone/email/maps app
10 | Email Subscription | Failed | Submitting an email to subscribe does nothing but reload the page | Not expected — should confirm subscription
11 | Google Maps Integration | Pass | Map on page works correctly via Google Maps | As expected
12 | Social Media Icons | Failed | Clicking social media icons in the About section footer reloads the page | Not expected — should open social media profiles
13 | Contact Us Page Nav | Pass | Pressing the Contact Us button in the top bar loads the Contact Us page | As expected
14 | Contact Form Validation | Pass | Entering incorrect information into contact form returns a validation error | As expected
15 | Email Validation Override | Failed | Providing a valid email removes the error even when phone number is incorrect | Not expected — phone number should also be validated
16 | Orders Page Navigation | Pass | Pressing the Orders button in the top bar loads the Orders page | As expected
17 | View Order Button | Failed | Pressing View Order reloads the page | Not expected — should display order details
18 | Track Shipment Button | Failed | Pressing Track Shipment reloads the page | Not expected — should open shipment tracking
19 | Buy It Again Button | Failed | Pressing Buy It Again reloads the page | Not expected — should add item to cart or go to product
20 | Request Return Button | Failed | Pressing Request a Return reloads the page | Not expected — should open returns process
21 | Top Right Icons | Failed | Pressing any of the three icons in the top right reloads the page on every page | Not expected — icons should perform their respective actions
22 | Home Button Navigation | Pass | Pressing the Home button in the top bar sends user back to the home page | As expected